## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
57 | 12 | 32 | 0.375
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2020-02-24 | 28 |  | 3 | 34 | 57 | 0 | 3 | 0 | 54 | 0.088235
2020-03-09 | 20 |  | 2 | 24 | 54 | 3 | 5 | 34 | 52 | 0.086207
2020-03-23 | 32 |  | 7 | 40 | 52 | 5 | 12 | 58 | 45 | 0.12245
2020-04-06 | 28 |  | 0 | 0 | 45 | 12 | 12 | 98 | 45 | 0.12245
2020-04-20 | 40 |  | 2 | 15 | 45 | 12 | 14 | 98 | 43 | 0.12389
2020-05-04 | 28 |  | 6 | 40 | 43 | 14 | 20 | 113 | 37 | 0.13072
2020-05-18 | 24 |  |  |  | 37 | 20 | 20 | 153 | 33.8627 | 0.13072
2020-06-01 | 24 |  |  |  | 33.8627 | 20 | 20 | 153 | 30.7255 | 0.13072
2020-06-15 | 24 |  |  |  | 30.7255 | 20 | 20 | 153 | 27.5882 | 0.13072
2020-06-29 | 24 |  |  |  | 27.5882 | 20 | 20 | 153 | 24.451 | 0.13072
2020-07-13 | 0 |  |  |  | 24.451 | 20 | 20 | 153 | 24.451 | 0.13072
2020-07-27 | 0 |  |  |  | 24.451 | 20 | 20 | 153 | 24.451 | 0.13072
2020-08-10 | 0 |  |  |  | 24.451 | 20 | 20 | 153 | 24.451 | 0.13072
2020-08-24 | 0 |  |  |  | 24.451 | 20 | 20 | 153 | 24.451 | 0.13072
2020-09-07 | 24 |  |  |  | 24.451 | 20 | 20 | 153 | 21.3137 | 0.13072
2020-09-21 | 24 |  |  |  | 21.3137 | 20 | 20 | 153 | 18.1765 | 0.13072
2020-10-05 | 24 |  |  |  | 18.1765 | 20 | 20 | 153 | 15.0392 | 0.13072
2020-10-19 | 24 |  |  |  | 15.0392 | 20 | 20 | 153 | 11.902 | 0.13072
2020-11-02 | 24 |  |  |  | 11.902 | 20 | 20 | 153 | 8.7647 | 0.13072
2020-11-16 | 24 |  |  |  | 8.7647 | 20 | 20 | 153 | 5.6275 | 0.13072
2020-11-30 | 24 |  |  |  | 5.6275 | 20 | 20 | 153 | 2.4902 | 0.13072
2020-12-14 | 24 |  |  |  | 2.4902 | 20 | 20 | 153 | 0 | 0.13072
2020-12-28 | 24 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-01-11 | 24 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-01-25 | 24 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-02-08 | 24 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-02-22 | 24 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-03-08 | 24 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-03-22 | 24 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-04-05 | 24 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-04-19 | 24 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-05-03 | 24 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-05-17 | 24 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-05-31 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-06-14 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-06-28 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-07-12 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-07-26 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-08-09 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-08-23 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-09-06 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-09-20 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-10-04 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-10-18 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-11-01 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
2021-11-15 | 0 |  |  |  | 0 | 20 | 20 | 153 | 0 | 0.13072
| 536 |  | 3.3333 | 25.5
Formulas:
Open Story Points = [Open Story Points, row above]+14