## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
70 | 12 | 32 | 0.375
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2020-02-24 | 28 |  | 3 | 34 | 70 | 0 | 3 | 0 | 67 | 0.088235
2020-03-09 | 20 |  | 2 | 24 | 67 | 3 | 5 | 34 | 65 | 0.086207
2020-03-23 | 32 |  | 0 | 40 | 65 | 5 | 5 | 58 | 65 | 0.05102
2020-04-06 | 28 |  | 0 | 0 | 65 | 5 | 5 | 98 | 65 | 0.05102
2020-04-20 | 18 |  | 2 | 20 | 65 | 5 | 7 | 98 | 63 | 0.059322
2020-05-04 | 28 |  | 3 | 40 | 63 | 7 | 10 | 118 | 60 | 0.063291
2020-05-18 | 24 |  | 3 | 24 | 60 | 10 | 13 | 158 | 57 | 0.071429
2020-06-01 | 24 |  |  |  | 57 | 13 | 13 | 182 | 55.2857 | 0.071429
2020-06-15 | 24 |  |  |  | 55.2857 | 13 | 13 | 182 | 53.5714 | 0.071429
2020-06-29 | 24 |  |  |  | 53.5714 | 13 | 13 | 182 | 51.8571 | 0.071429
2020-07-13 | 0 |  |  |  | 51.8571 | 13 | 13 | 182 | 51.8571 | 0.071429
2020-07-27 | 0 |  |  |  | 51.8571 | 13 | 13 | 182 | 51.8571 | 0.071429
2020-08-10 | 0 |  |  |  | 51.8571 | 13 | 13 | 182 | 51.8571 | 0.071429
2020-08-24 | 0 |  |  |  | 51.8571 | 13 | 13 | 182 | 51.8571 | 0.071429
2020-09-07 | 24 |  |  |  | 51.8571 | 13 | 13 | 182 | 50.1429 | 0.071429
2020-09-21 | 24 |  |  |  | 50.1429 | 13 | 13 | 182 | 48.4286 | 0.071429
2020-10-05 | 24 |  |  |  | 48.4286 | 13 | 13 | 182 | 46.7143 | 0.071429
2020-10-19 | 24 |  |  |  | 46.7143 | 13 | 13 | 182 | 45 | 0.071429
2020-11-02 | 24 |  |  |  | 45 | 13 | 13 | 182 | 43.2857 | 0.071429
2020-11-16 | 24 |  |  |  | 43.2857 | 13 | 13 | 182 | 41.5714 | 0.071429
2020-11-30 | 24 |  |  |  | 41.5714 | 13 | 13 | 182 | 39.8571 | 0.071429
2020-12-14 | 24 |  |  |  | 39.8571 | 13 | 13 | 182 | 38.1429 | 0.071429
2020-12-28 | 24 |  |  |  | 38.1429 | 13 | 13 | 182 | 36.4286 | 0.071429
2021-01-11 | 24 |  |  |  | 36.4286 | 13 | 13 | 182 | 34.7143 | 0.071429
2021-01-25 | 24 |  |  |  | 34.7143 | 13 | 13 | 182 | 33 | 0.071429
2021-02-08 | 24 |  |  |  | 33 | 13 | 13 | 182 | 31.2857 | 0.071429
2021-02-22 | 24 |  |  |  | 31.2857 | 13 | 13 | 182 | 29.5714 | 0.071429
2021-03-08 | 24 |  |  |  | 29.5714 | 13 | 13 | 182 | 27.8571 | 0.071429
2021-03-22 | 24 |  |  |  | 27.8571 | 13 | 13 | 182 | 26.1429 | 0.071429
2021-04-05 | 24 |  |  |  | 26.1429 | 13 | 13 | 182 | 24.4286 | 0.071429
2021-04-19 | 24 |  |  |  | 24.4286 | 13 | 13 | 182 | 22.7143 | 0.071429
2021-05-03 | 24 |  |  |  | 22.7143 | 13 | 13 | 182 | 21 | 0.071429
2021-05-17 | 24 |  |  |  | 21 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-05-31 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-06-14 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-06-28 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-07-12 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-07-26 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-08-09 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-08-23 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-09-06 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-09-20 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-10-04 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-10-18 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-11-01 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
2021-11-15 | 0 |  |  |  | 19.2857 | 13 | 13 | 182 | 19.2857 | 0.071429
| 514 |  | 1.8571 | 26
Formulas:
Open Story Points = [Open Story Points, row above]+14