## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
57 | 5 | 16 | 0.3125
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2020-02-24 | 7 |  | 3 | 10 | 57 | 0 | 3 | 0 | 54 | 0.3
2020-03-02 | 6 |  | 2 | 6 | 54 | 3 | 5 | 10 | 52 | 0.3125
2020-03-16 | 18 |  | 5 | 20 | 52 | 5 | 10 | 16 | 47 | 0.27778
2020-04-06 | 18 |  | 2 | 20 | 47 | 10 | 12 | 36 | 45 | 0.21429
2020-04-27 | 18 |  | 2 | 20 | 45 | 12 | 14 | 56 | 43 | 0.18421
2020-05-18 | 18 |  | 5 | 20 | 43 | 14 | 19 | 76 | 38 | 0.19792
2020-06-15 | 18 |  |  |  | 38 | 19 | 19 | 96 | 34.4375 | 0.19792
2020-06-22 | 18 |  |  |  | 34.4375 | 19 | 19 | 96 | 30.875 | 0.19792
2020-06-29 | 18 |  |  |  | 30.875 | 19 | 19 | 96 | 27.3125 | 0.19792
| 139 |  | 3.1667 | 16
Formulas:
Open Story Points = [Open Story Points, row above]+7