## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
57 | 3 | 20 | 0
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2020-02-24 | 7 | 0 | 0 | 10 | 57 | 0 | 0 | 0 | 54 | 0
2020-03-02 | 3 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 52 | #DIV/0!
2020-03-16 | 10 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 44 | #DIV/0!
2020-04-06 | 18 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 23 | #DIV/0!
2020-04-27 | 13 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 10 | #DIV/0!
2020-05-18 | 8 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 5 | #DIV/0!
2020-06-15 | 8 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | #DIV/0!
| 67 | 0 | 0 | 1.4286